## Slide 1: Rift Wingsuit
Sebastian Nickel, Jonas Kleinkauf, Andreas Dietze, Manuel Schmitt, Sascha Ibach

## Slide 2: Content
Technical features and updates
New assets and logics
Updated milestones

## Slide 3: Updates Kinect
Solved Kinect problems
  Hardware sided (USB)
New kinect package
  Supporting Kinect V1/2
Optimized processing of Kinect outputs
Hierarchy und Prefabs
Notes: Rotation-Lock-X => Es kann nicht übersteuert werden

## Slide 4: Oculus Rift
Some problems with new SDKs
Search solutions
Re-implementation

## Slide 5: Responsibilities (Assistent)
Oculus DK2 / Vive
  Sascha Ibach (A. Dietze)
Kinect V1/V2
  Andreas Dietze (S. Nickel)
Flyphysics
  Sebastian Nickel (A. Dietze)
Player model
  Jonas Kleinkauf (S. Ibach)
World and ambiance
  Jonas Kleinkauf (M. Schmitt)
Post processing
  Manuel Schmitt (J.K., S.N.)
Audio
  Jonas Kleinkauf (A. Dietze)
Menues
  Manuel Schmitt (S.N., S.I.)
Gamelogics
  Jonas Kleinkauf (Comp. Grp.)
Documentation and User Guide
  Andreas Dietze (M.S., S.I.)
Simplified handling
  Sascha Ibach (A. Dietze)

## Slide 6: Milestone One (old)
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
05.12 – 05.19 | Clean up, git Kinect V2 Old state | Laws of aerodynamics | Terrain optimization Terrain generation | Working into the project and Unity Engine | Working into the project and Unity Engine
05.19 – 05.26 | Setup 06.10 Setup impr. New world assets | First model based on real physic laws | Obstacles Collision, Bonus Items, Updrafts | Creation of post-processing effects like bloom and blur | Working into Oculus and possible improvements
05.26 – 06.02 | Setup 06.10 Vive integr. (visula) | Continuing work on the flying physics model | NewLevel Creation using Terrain Generators | Creation of ambient-occlusion-light -map | Oculus improvements (Menu, …)

## Slide 7: Milestone One (updated)
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
05.12 – 05.19 | Clean up, git Kinect V2 Old state | Laws of aerodynamics |  |  | 
05.19 – 05.26 | Kinect V1/2 Setup impr. | First model based on real physic laws |  |  | 
05.26 – 06.02 | Kinect V1/2 (getting crazy) | Continuing work on the flying physics model |  |  | 

## Slide 8: Milestone Two (old)
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
06.02 – 06.09 | Vive inter. (haptic) Kinect impr. Balancing new features | Improve fly-physics model Error tolerance | Level Design, Programming Obstacle Placement, Player Path | Buffer for ao God-rays and/or atmos. scattering | Server-menue Oculus Shader-menue and controls
06.09 – 06.16 | Vive location setup, impr. Fly physics Doc | Add configuratable properties to flying-model | Secrets Collectibles World Refinement | Client-menu-structure Menue functionality | Game Interaction / - Logic / -Flow (Parachute landing, …)
06.16 – 06.23 | Fly physics Doc User Guide | Through testing of the flying physics | Player Model Rigging Texturing | Menue funct. Gamepad support | Buffer for GameLogic Playermodel

## Slide 9: Milestone Two (updated)
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
06.02 – 06.09 | Implem. new Kinect package Kinect V1/2 stable config Flight impr. | Improve fly-physics model Configurable Bugfixed fly-physics issues |  |  | 
06.09 – 06.16 | Flight impr. Oculus setup Setup 06.10 | Bugfixing Error handling |  |  | 
06.16 – 06.23 | Vive integr. tests  Fly physics support | Thorough Fly-Physics tests |  |  | 

## Slide 10: Exams
16.07.2016 - 30.07.2016 and 12.09.2016 - 24.09.2016
  Exam and preperation 23.06 - 30.07
  Sec. exam phase -> individual schedule

## Slide 11: Milestone Three (old)
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
08.01 – 08.08 | Fly physics User Guide Doc | Evaluation of open-source KinectV2 driver | Player Model Animations with User Input | User guide support | User guide (client)
08.08 – 08.16 | Client cam Client audio Client handl. | Assisting with the menu struct. e.g.: possible improvements | Integration World + Game objects by project team | Documen-tation support | Documen-tation (client)
08.16 – 24.08 | Client improvement buffer | Buffer; Overall testing („Bug hunting“) | Background Music and Sound Effects | Buffer for any relevant work | Buffer for any relevant work
08.24 – 09.14 | Buffer (fly physics, game logics, …) | Buffer (fly physics, game logics, assistant) | Buffer (fly physics, game logics, assistant) | Buffer for any relevant work | Buffer for any relevant work

## Slide 12: Milestone Three (updated)
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
08.01 – 08.08 | Doc User Guide Client impr. | Assisting with the menu struct. e.g.: possible improvements |  |  | 
08.08 – 08.16 | Client cam Client audio Client handl. | „The helping hand for emergencies“ |  |  | 
08.16 – 24.08 | Client improvement buffer | Buffer; Overall testing („Bug hunting“) |  |  | 
08.24 – 09.14 | Buffer (fly physics, game logics, ..) | Buffer (fly physics, game logics, assistant) |  |  | 

## Slide 13: Risks
Fly physics - math too complex/complicated
Arm network transmission
Post-effects too performance- consuming (scattering, ambient occlusion)
Realtime Performance Issues for slower PCs (Graphics Settings?)
AR Performance Problems
Menue handling (Oculus)
Gesture control problems (APIs for Vive not tested yet, currently unstable APIs for Kinect?)
Suitable for HS-Lan and Open-Lab
Ofc: Illness of Project Members (workload balancing)

## Slide 14: Github Version Control
Old project source
https://github.com/andreasdietze/Rift-Wingsuit.git
New project source
https://github.com/andreasdietze/Rift-WingsuitV2.git

## Slide 15: Thanks for your attention 