## Slide 1: Rift Wingsuit
Sebastian Nickel, Jonas Kleinkauf, Andreas Dietze, Manuel Schmitt, Sascha Ibach

## Slide 2: Content
Technical features and updates
New assets and logics
Updated milestones

## Slide 3: Updates Kinect
Solved Kinect problems
  Hardware sided (USB)
New kinect package
  Supporting Kinect V1/2
Optimized processing of Kinect outputs
Hierarchy und Prefabs
Notes: Rotation-Lock-X => Es kann nicht übersteuert werden

## Slide 4: Oculus Rift
Some problems with new SDKs
Search solutions
Re-implementation

## Slide 5: Responsibilities (Assistent)
Oculus DK2 / Vive
  Sascha Ibach (A. Dietze)
Kinect V1/V2
  Andreas Dietze (S. Nickel)
Flyphysics
  Sebastian Nickel (A. Dietze)
Player model
  Jonas Kleinkauf (S. Ibach)
World and ambiance
  Jonas Kleinkauf (M. Schmitt)
Post processing
  Manuel Schmitt (J.K., S.N.)
Audio
  Jonas Kleinkauf (A. Dietze)
Menues
  Manuel Schmitt (S.N., S.I.)
Gamelogics
  Jonas Kleinkauf (Comp. Grp.)
Documentation and User Guide
  Andreas Dietze (M.S., S.I.)
Simplified handling
  Sascha Ibach (A. Dietze)

## Slide 6: Milestone One
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
05.12 – 05.19 | Clean up, git Kinect V2 Old state | Laws of aerodynamics | Terrain optimization Terrain generation | Working into the project and Unity Engine | Working into the project and Unity Engine
05.19 – 05.26 | Setup 06.10 Setup impr. New world assets | First aerodynamic (ad) model | Obstacles Collision, Bonus Items, Updrafts | Creation of post-processing effects like bloom and blur | Working into Oculus and possible improvements
05.26 – 06.02 | Setup 06.10 Vive integr. (visula) | Continue work ad. model | NewLevel Creation using Terrain Generators | Creation of ambient-occlusion-light -map | Oculus improvements (Menu, …)

## Slide 7: Milestone One
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
05.12 – 05.19 | Clean up, git Kinect V2 Old state |  |  |  | 
05.19 – 05.26 | Kinect V1/2 Setup impr. |  |  |  | 
05.26 – 06.02 | Kinect V1/2 (getting crazy) |  |  |  | 

## Slide 8: Milestone Two
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
06.02 – 06.09 | Vive inter. (haptic) Kinect impr. Balancing new features | Increase flyphysics Error tolerance | Level Design, Programming Obstacle Placement, Player Path | Buffer for ao God-rays and/or atmos. scattering | Server-menue Oculus Shader-menue and controls
06.09 – 06.16 | Vive location setup, impr. Fly physics Doc | Add configuratable properties to flying-model | Secrets Collectibles World Refinement | Client-menu-structure Menue functionality | Game Interaction / - Logic / -Flow (Parachute landing, …)
06.16 – 06.23 | Fly physics Doc User Guide | Through testing of the flying physics | Player Model Rigging Texturing | Menue funct. Gamepad support | Buffer for GameLogic Playermodel

## Slide 9: Milestone Two
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
06.02 – 06.09 | Implem. new Kinect package Kinect V1/2 stable config Flight impr. |  |  |  | 
06.09 – 06.16 | Flight impr. Oculus setup Setup 06.10 |  |  |  | 
06.16 – 06.23 | Vive integr. tests  Fly physics support |  |  |  | 

## Slide 10: Exams
16.07.2016 - 30.07.2016 and 12.09.2016 - 24.09.2016
  Exam and preperation 23.06 - 30.07
  Sec. exam phase -> individual schedule

## Slide 11: Milestone Three
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
08.01 – 08.08 | Fly physics User Guide Doc | Evaluation of open-source KinectV2 driver | Player Model Animations with User Input | User guide support | User guide (client)
08.08 – 08.16 | Client cam Client audio Client handl. | Assisting with the menu struct. e.g.: possible improvements | Integration World + Game objects by project team | Documen-tation support | Documen-tation (client)
08.16 – 24.08 | Client improvement buffer | Buffer; Overall testing („Bug hunting“) | Background Music and Sound Effects | Buffer for any relevant work | Buffer for any relevant work
08.24 – 09.14 | Buffer (fly physics, game logics, …) | Buffer (fly physics, game logics, assistant) | Buffer (fly physics, game logics, assistant) | Buffer for any relevant work | Buffer for any relevant work

## Slide 12: Milestone Three
Week | Andras Dietze | Sebastian Nickel | Jonas Kleinkauf | Manuel Schmitt | Sascha Ibach
08.01 – 08.08 | Doc User Guide Client impr. |  |  |  | 
08.08 – 08.16 | Client cam Client audio Client handl. |  |  |  | 
08.16 – 24.08 | Client improvement buffer |  |  |  | 
08.24 – 09.14 | Buffer (fly physics, game logics, ..) |  |  |  | 

## Slide 13: Risks
Fly physics - math too complex/complicated
Arm network transmission
Post-effects too performance- consuming (scattering, ambient occlusion)
Realtime Performance Issues for slower PCs (Graphics Settings?)
AR Performance Problems
Menue handling (Oculus)
Gesture control problems (APIs for Vive not tested yet, currently unstable APIs for Kinect?)
Suitable for HS-Lan and Open-Lab
Ofc: Illness of Project Members (workload balancing)

## Slide 14: Github Version Control
Old project source
https://github.com/andreasdietze/Rift-Wingsuit.git
New project source
https://github.com/andreasdietze/Rift-WingsuitV2.git

## Slide 15: Thanks for your attention 