## Slide 1: Rift Wingsuit
Sebastian Nickel, Jonas Kleinkauf, Andreas Dietze, Manuel Schmitt, Sascha Ibach

## Slide 2: Content
Summary
Project presentation (pp)
Project extension
Responsibilities
Milestones
Risks

## Slide 3: Summary
Rift Wingsuit offers a realistic world from the perspective of wingsuit sport. Experience the feeling of total freedom, using the Oculus Rift head-mounted display in combination with guesture control for the protagonist.
Wingsuit valley awaits you !

## Slide 4: pp - World
Developed with Unity 3D
Deployed assets
Own part
  Scripts
  Vegetation
  Water
  Ambiance

## Slide 5: pp – Kinect control
Player control by arm tracking(Kinect):
  X-Axis (Pitch)
    Forward / Back
  Y-Axis(Yaw)
    Up / Down
Right-Arm-Tracking
Notes: Rotation-Lock-X => Es kann nicht übersteuert werden

## Slide 6: pp - Oculus Rift support
Using head rotation for first-person-view
To make the game more immversive

## Slide 7: pp - Server and client
Only used as a spectator client
Used for demonstrational purposes
Used to get a better view of the player´s perspective (FPV-Transmission)

## Slide 8: Project extensions
Fly physics
Player model (visible arm movement)
Effect-Events (flying through a bridge)
Rework and/or improve kinect control
Graphical update
  Post-effects (radial blur)
  Some terrain and world improvements
    Clouds
    Better lighting

## Slide 9: Project extensions
Client improvment
  Additional camera styles
    Some fly-by-camera styles
    Improve existing camera styles
Menues and simplified handling
  Game flow (menues and gesture control – maybe makey makey)
  Improved construction concept
    Location of kinect, player, spectators, etc.
    Simplified handling of the game and it´s features
  Documentation
    Frameworks, Packages
    User Guide (how to get it running)
  Goal: suitable for HS-LAN and Open-Lab (HS-Informationstage)

## Slide 10: Responsibilities (Assistent)
Oculus DK2 / Vive
  Sascha Ibach (A. Dietze)
Kinect V1/V2
  Andreas Dietze (S. Nickel)
Flyphysics
  Sebastian Nickel (A. Dietze)
Player model
  Jonas Kleinkauf (S. Ibach)
World and ambiance
  Jonas Kleinkauf (M. Schmitt)
Post processing
  Manuel Schmitt (J.K., S.N)
Audio
  Jonas Kleinkauf (A. Dietze)
Menues
  Manuel Schmitt (S. Nickel)
Gamelogics
  Jonas Kleinkauf (Comp. Grp.)
Documentation and User Guide
  Andreas Dietze (M. Schmitt)
Simplified handling
  Sascha Ibach (wer?)

## Slide 11: Milestone 1
Week | Andreas Dietze
05.12 – 05.19 | Project clean up and initial git uplaod Compatibility test with Kinect V2 (min win 8 :/ ) Setup to old working state with client
05.19 – 05.26 | Setup project (interaction laboratory) for 09.06 Location and setup improvement Check out new world assets
05.26 – 06.02 | Setup project (interaction laboratory) for 09.06 Vive integration, Vive project functionality (visual)

## Slide 12: Milestone 1
Week | Jonas Kleinkauf
05.12 – 05.19 | Unity Terrain Optimizations, Terrain Generation Tests?
05.19 – 05.26 | Obstacle Programming: Action Collision, Bonus Items, Updrafts
05.26 – 06.02 | New Level Creation using Terrain Generators

## Slide 13: Milestone 1
Week | Manuel Schmitt
05.12 – 05.19 | Working into the project and Unity Engine
05.19 – 05.26 | Creation of post-processing effects like bloom and blur
05.26 – 06.02 | Creation of ambient-occlusion-light -map

## Slide 14: Milestone 1
Week | Sebastian Nickel
05.12 – 05.19 | Raw comprehension of the laws of aerodynamics
05.19 – 05.26 | Prototyping first aerodynamic model for the game
05.26 – 06.02 | Continue to work on prototype

## Slide 15: Milestone 1
Week | Sascha Ibach
05.12 – 05.19 | Working into the project and Unity Engine
05.19 – 05.26 | Working into Oculus and possible improvements
05.26 – 06.02 | Oculus improvements (Menu, …)

## Slide 16: Milestone 2
Week | Andreas Dietze
06.02 – 06.09 | Vive project functionality (haptic and gesture tests) Kinect improvement Balancing the new developed features
06.09 – 06.16 | Vive location and setup improvement Fly physics Documentation
06.16 – 06.23 | Fly physics Documentation User Guide

## Slide 17: Milestone 2
Week | Jonas Kleinkauf
06.02 – 06.09 | Level Design + Programming, Obstacle Placement, Player Path
06.09 – 06.16 | Make the Game more interesting to Play: Secrets, Collectibles, World Refinement
06.16 – 06.23 | Player Model refinement, Rigging, Texturing

## Slide 18: Milestone 2
Week | Manuel Schmitt
06.02 – 06.09 | Buffer for ambient-occlusion Alternative: Implementation of light effects like god-rays or atmospheric scattering
06.09 – 06.16 | Implementation of client-menu-structure
06.16 – 06.23 | Implementation of spectator-client-menu

## Slide 19: Milestone 2
Week | Sebastian Nickel
06.02 – 06.09 | Increase flexibility of established fly-physics prototype Error tolerence, …
06.09 – 06.16 | Add configuratable properties to flying-model for an even more realistic experience Actual height of player, weight, …
06.16 – 06.23 | Thorough testing of the flying physics

## Slide 20: Milestone 2
Week | Sascha Ibach
06.02 – 06.09 | Menus (Controls, Oculus (Shader))
06.09 – 06.16 | Game Interaction / - Logic / -Flow (Parachute landing, …)
06.16 – 06.23 | Buffer for GameLogic Playermodel

## Slide 21: Exams
16.07.2016 - 30.07.2016 and 12.09.2016 - 24.09.2016
  Exam and preperation 23.06 - 30.07
  Sec. exam phase -> individual schedule

## Slide 22: Milestone 3
Week | Andreas Dietze
08.01 – 08.08 | Fly physics User Guide
08.08 – 08.16 (less time) | Client cam views Client audio Client handling improvement
08.16 – 24.08 | Client improvement buffer
08.24 – 09.14 | Buffer until project end (Fly physics, game logics, assistant)

## Slide 23: Milestone 3
Week | Jonas Kleinkauf
08.01 – 08.08 | Player Model Animations, Integrating Animations with User Input
08.08 – 08.16 | Integration of new World + Game objects other works of the project team
08.16 – 24.08 | Producing Background Music and Sound Effects
08.24 – 09.14 | Buffer until project end (Fly physics, game logics, assistant)

## Slide 24: Milestone 3
Week | Manuel Schmitt
08.01 – 08.08 | Creation of a users guide for the project
08.08 – 08.16 | Creation of a project documentation
08.16 – 24.08 | Buffer for any relevant work
08.24 – 09.14 | Buffer for any relevant work

## Slide 25: Milestone 3
Week | Sebastian Nickel
08.01 – 08.08 | Evaluation of “Freenect2”, an open-source KinectV2 driver
08.08 – 08.16 | Assisting with the menu structure-related work e.g.: possible improvements, testing, …
08.16 – 24.08 | Buffer for related work; Overall testing („Bug hunting“)
08.24 – 09.14 | Buffer until project end (Fly physics, game logics, assistant)

## Slide 26: Milestone 3
Week | Sascha Ibach
08.01 – 08.08 | Creation of a users guide for the project
08.08 – 08.16 | Creation of a project documentation
08.16 – 24.08 | Buffer for related work
08.24 – 09.14 | Buffer for related work

## Slide 27: Risks
Fly physics - math too complex/complicated
Arm network transmission
Post-effects too performance- consuming (scattering, ambient occlusion)
Realtime Performance Issues for slower PCs (Graphics Settings?)
AR Performance Problems
Menue handling (Oculus)
Gesture control problems (APIs for Vive not tested yet, currently unstable APIs for Kinect?)
Suitable for HS-Lan and Open-Lab
Ofc: Illness of Project Members (workload balancing)

## Slide 28: Github Version Control
Old project source
https://github.com/andreasdietze/Rift-Wingsuit.git
New project source
https://github.com/andreasdietze/Rift-WingsuitV2.git

## Slide 29: Thanks for your attention 